## Employee
# | Sub-module | Details | Status | Remarks
1 | My 201 | OPEN SEASON - allow employees to update their records (Contacts, Personal, and family) | Pending | Needed date May 24 to 31
2 | Dashboard | Feeds comments not working | Pending
3 | 201 | Cron for family dependent to tag if more than 22 years old and not PWD then dependent should tag as no, and dropdown for tax code should update automatically | Pending
4 | 201 | Editing of Profile not working (adding of Interest) | Pending
5 | Employee Directory | Employee can view email, phone/local, About Me of all employees (my profile - except mobile, bday, location and Status) | Pending | Request by Jorge
6 | Master | Add a new coordinator (copy a coordinator role/access) | For user orientation?
7 | Certificate of Employment | with tenure and with salary | Pending'

## Timekeeping
# | Sub-module | Details | Status | Remarks
1 |  |  | Pending
2 | DTR Processing | Undetime In/Out - computation of undetime in/out must be based on the approved application. For Manages and up, undertime is for record purpose only (No deduction on payroll) | Pending
3 | Master | Holiday - Option to copy all holiday in a year | Pending
4 | Leave Balance - Admin | UI for manual entry and viewing of leave credit (accrual) | Pending
5 | Overtime | R&F min of 1HR Supervisor min 2hrs reg day / restday, day-off and holiday 4hs" | ?
6 | Home Leave Forfeiture | Unused home leave/s shall be consumed up to the end of the calendar year only. Date of Forfeiture: Every January 1 | ?
7 | Home Leave Conversion | Procedure on conversion of unused home leave (same as LIP) | test concern | pinapagana palang ung existing. See details on consolidated log
8 | LIP Conversion | leave conversion module for unused leave (default value is 10 but editable by user) minimum tenure for convertion is at least 6months of continuous service from probationary period | test concern | pinapagana palang ung existing. See details on consolidated log
9 | LIP Forfeiture | Unused hLIP Credit/s shall be consumed up to the march 31 of the following month. Date of Forfeiture: Every April 1 | ?
10 | Work Schedule; New UI | For Enhancement | For Discussion
11 | Work Schedule not scrolling | Scroll bar for list of employee sometimes not loading (for checking mozilla browser) Using search employee, default/selected shift did not reflected because system load the weekly sched instead of shift. | For Validation
12 | Shifts in work schedule is not arranged properly | Work calendar - list os shift must be sorted by description (a - 1)
13 | Perfect Attendance Report | Perfect Attendance Report | Pending | Ask for sample format and formula /policy for perfect attendance

## Payroll
# | Sub-module | Details | Status | Remarks

## Code of Conduct
# | Sub-module | Details | Status | Remarks
1 | Reports | IR Reports | Pending
2 | DA | DA Form Printout |  | AHI to use our template but waiting for details of any changes
3
4

## Movement
# | Sub-module | Details | Status | Remarks
1 | Notification | issue on sp_dashboard_notification regarding on lenght of content | Pending
2 | Salary Field | current salary and new salary must be auto comma and 2 decimal. | Pending
3 | Transfer | Add company on transfer movement | Pending
4 | Approval process | Additional approver on HR (multiple approver) | Pending
5 | Resignation | once resignation movement was approved by the final approver nagccreate na agad sa clearance listing (no effectivity date w/c display 1970 kaya mali ung turn around date ) dapat ata turn around time ang label | Pending | This is also connected to AHI request regaring HR approval Process.
6 | movement printing | movement form | ongoing

## Clearance
# | Sub-module | Details | Status | Remarks
1 | Clearance printing | Clearance Sigantories Form | On-going
2 | Clearance Mange | Add accountabilities (add item button) and attachment button | Pending | add some minor for adjustment on CLEARANCE test result 052117.doc
3 | Exit interview printing | Exit interview printing | Pending
4 | Quitclaim Printing | Quitclaim Printing | Pending
5 | Certificate of Employment | Certificate of Employment | Pending