## Sheet1
Emplopad Remaining Modules Project Timeline
as of September 8, 2017
No. | Modules | Responsible | Target Date | Date Delivered | Status | Remarks
1 | Employee Movement and Clearance |  |  |  | On-going
| Data Gathering | Teemworx and AHI |  |  | Done
| Submission of Mock-up Design to AHI | Teemworx |  | 2017-07-04 | Done
| Mock-up Design for AHI Signature | AHI |  | 2017-08-23 | Done | Signed by Ms. Lee
| Development | Teemworx | 2017-09-08 |  | On-going
| System Presentation | Teemworx and AHI | 2017-09-12
| UAT | AHI | 2017-09-15
| UAT Acceptance | AHI | 2017-09-15
2 | Recruitment |  |  |  | On-going
| Data Gathering | Teemworx and AHI |  |  | Done
| Submission of Mock-up Design to AHI | Teemworx |  | 2017-08-25 | Done
| Mock-up Design for AHI Signature | AHI | 09/11/2017 |  | Pending | c/o Ms. Amyra
| Development | Teemworx | 2017-09-15
| System Presentation | Teemworx and AHI | 2017-09-19
| UAT | AHI | 2017-09-22
| UAT Acceptance | AHI | 2017-09-22
3 | Training and Development |  |  |  | On-going
| Data Gathering | Teemworx and AHI |  |  | Done
| Submission of Mock-up Design to AHI | Teemworx | 2017-09-08 | 2017-09-07 | Done
| Mock-up Design for AHI Signature | AHI | 2017-09-12 |  |  | c/o Ms. Lissa
| Development | Teemworx | 2017-09-22
| System Presentation | Teemworx and AHI | 2017-09-26
| UAT | AHI | 2017-09-29
| UAT Acceptance | AHI | 2017-09-29
4 | Performance Appraisal
| Data Gathering | Teemworx and AHI |  | 2017-09-05 | Done
| Submission of Mock-up Design to AHI | Teemworx | 2017-09-13
| Mock-up Design for AHI Signature | AHI | 2017-09-19 |  |  | c/o Ms. Lissa
| Development | Teemworx | 2017-09-29
| System Presentation | Teemworx and AHI | 2017-10-03
| UAT | AHI | 2017-10-06
| UAT Acceptance | AHI | 2017-10-06