## Sheet1
2017-10-26
10AM, KDR
Attendees: WME, NCC, Joel Mendoza, Rommel Lozada, Tirso Garcia, Lee, Lissa
NO | AGENDA | PARTICULARS | RESOLUTIONS | RESPONSIBLE | ACTION | DATE DUE | TARGET LIVE
1 | Performance Appraisal Report | Target setting/planning remove out for the users | All forms pre-created/pre-determined | Teemworx | For determination of schedule and to be discussed with AbHI Team
|  | Access on target setting of KPIs and KRAs will only be given to HRD | Fixed 60% for TCPAs/Work Output, 20% Self Discipline, 20% Teamwork.
|  | At least 20% of performance indicator shall be given to immediate superior | Ratings for special assigments incorporated in 60% work output.
|  | Opening of appraisal period | Access will only be given to HRD
|  | Closing of PAR in case of non acceptance of employee | Employee needs to fill in the remarks field in case he will not accept it.
|  | Closing of PAR Season | Automatic closing will be implemented however, HRD may manually re-open the PAR season.
|  | PARs for Sups and Managers | Fixed 20% each for POLC, 10% Self Discipline, 10% Teamwork
|  | Generating of reports | Generation per property and quarterly/annually with adjective rating or summary of submitted PARs (check or no check). Filtering includes property, period of appraisal, and rating.
2 | Movement | Request for movement should only be received by assigned HR Staff handling the property with movement but request was received by all HR Staff. | Upon checking of Teemworx, this shouldn't be experienced in the live environment. | Teemworx and AbHI | Modification then UAT | Update to UAT - 11/3/17 UAT - 11/6/17 | 2017-11-20
|  | Remarks' in movement | Remarks only made by HRD should reflect in the printed EMR. For employee movement, remarks given by the requisitioning employee for reference/justification only. Movement remarks change to Justification. Remarks in Employee Movement change to Reason. Remove 'Salary Increase Remarks' Remove 'description' in the EMR
3 | Training | Over the annual training budget | Approver can still approve the request/application | Teemworx | For determination of schedule and to be discussed with AbHI Team
|  | Masterlist of training | Predetermined, HR to add new seminar/training as per request Internal ticketing system will be implemented in collaboration with ICT.
|  | Training fee indicated in online request | HR can modify training cost based on training fee, transpo, meal, accommodation, and daily rate of the employee.
|  | HR fields in training request | Include 'Cancel' button
|  | Training bond | Automatically computed by the system as per company's policy
|  | Request for external training form print out | No need for printing; system record will suffice
|  | Approval of request in HR | HR staff to determine approver of the request
|  | Feedback form | Pre-requisite for the next request.
4 | Recruitment | Hiring type | Include 'rehire' in the options | Teemworx and AbHI | Modification then UAT | Update to UAT - 11/3/17 UAT - 11/6/17 | 2017-11-20
|  | Attachment field in the request | Needed only for hiring new positions
|  | Kiosk for applicants | For implementation of HRD
|  | Interview details | Include edit option that can be used by HRD
|  | Job Offer Template | Editable
|  | Pre-employment requirements | Can be manually transferred to creating 201 file
5 | Admin Access | Employee certificate for managers | NCC and RPC to finalize process owner 10/30/17. | HRD |  | 2017-10-30
|  | IT Access | Remove payroll access of IT
|  | Finalize Admin Access | Should be signed by NCC and WME
6 | Code of conduct | Link of offenses and approver | For checking | Teemworx and AbHI | Modification then UAT | Update to UAT - 11/3/17 UAT - 11/6/17 | 2017-11-20